# SECTION 4: MVP1 SPRINT ROADMAP

Timeline: 3 months (12 weeks) | 6 two-week sprints

Velocity Planning: S1-S2 at 60% capacity (ramp-up), S3-S4 at 80%, S5-S6 at 100%

## 4.1 Sprint Overview Table

| Sprint | Dates | Theme | Sprint Goal | Story Points | Stories |
| --- | --- | --- | --- | --- | --- |
| S1 | Week 1-2 | Foundation | User can register, login, and browse products | 55 | 15 |
| S2 | Week 3-4 | Product Discovery | User can search, filter, and view product details | 65 | 14 |
| S3 | Week 5-6 | Shopping Cart | User can add items to cart and manage addresses | 70 | 16 |
| S4 | Week 7-8 | Checkout | User can complete checkout and place orders | 75 | 14 |
| S5 | Week 9-10 | Order Management | User can track orders and receive notifications | 70 | 12 |
| S6 | Week 11-12 | Polish & Launch | System is QA-verified and production-ready | 45 | 8 |

Total MVP1: 380 Story Points | 79 User Stories

## 4.2 Sprint 1: Foundation

Duration: Week 1-2 | Points: 55

Sprint Goal: Users can register, login, and browse the product catalog with categories.

Stories Included:

| ID | Title | Points | Team | Priority |
| --- | --- | --- | --- | --- |
| SS-AUTH-001 | Email Registration with OTP | 8 | BE+FE | Must Have |
| SS-AUTH-002 | Email/Password Login | 5 | BE+FE | Must Have |
| SS-AUTH-005 | Password Reset Flow | 5 | BE+FE | Must Have |
| SS-AUTH-006 | Token Refresh | 5 | BE+FE | Must Have |
| SS-AUTH-007 | Logout with Token Blacklisting | 3 | BE+FE | Must Have |
| SS-AUTH-011 | Arabic Language Registration Form | 3 | FE | Must Have |
| SS-PROD-001 | Browse Products with Pagination | 5 | BE+FE | Must Have |
| SS-CAT-001 | Browse Categories via Mega Menu | 8 | FE | Must Have |
| SS-CAT-004 | Featured Categories on Homepage | 3 | BE+FE | Must Have |
| UX-001 | Design System Setup (Material + Tailwind) | 5 | UX | Must Have |
| INFRA-001 | CI/CD Pipeline Setup | 5 | DevOps | Must Have |

Sprint 1 Demo Scenarios:

- Demo 1: User registers with email, receives OTP, verifies account

- Demo 2: User logs in, sees JWT token handling (dev tools)

- Demo 3: User browses mega menu, sees categories

- Demo 4: Homepage loads with featured categories and product grid

Release Notes Draft:

v0.1.0-alpha: Core authentication (email registration with OTP, login, password reset, logout). Product catalog with pagination. Category navigation with mega menu. Arabic RTL support foundation.

## 4.3 Sprint 2: Product Discovery

Duration: Week 3-4 | Points: 65

Sprint Goal: Users can search products, apply filters, and view detailed product pages.

Stories Included:

| ID | Title | Points | Team | Priority |
| --- | --- | --- | --- | --- |
| SS-AUTH-003 | Google OAuth 2.0 Login | 8 | BE+FE | Should Have |
| SS-AUTH-004 | Facebook OAuth 2.0 Login | 8 | BE+FE | Should Have |
| SS-AUTH-008 | Login Attempt Tracking | 5 | BE | Must Have |
| SS-AUTH-010 | Remember Me Functionality | 3 | BE+FE | Should Have |
| SS-USER-001 | View Profile Information | 3 | BE+FE | Must Have |
| SS-USER-002 | Update Profile Information | 5 | BE+FE | Must Have |
| SS-USER-003 | Change Password | 5 | BE+FE | Must Have |
| SS-PROD-002 | Search Products | 8 | BE+FE | Must Have |
| SS-PROD-003 | Filter Products by Category | 5 | BE+FE | Must Have |
| SS-PROD-004 | Filter by Price Range | 5 | BE+FE | Must Have |
| SS-PROD-006 | Sort Products | 3 | BE+FE | Must Have |
| SS-PROD-007 | View Product Detail Page | 8 | BE+FE | Must Have |
| SS-CAT-002 | Category Page with Products | 5 | BE+FE | Must Have |
| SS-CAT-003 | Category Hierarchy Navigation | 5 | BE+FE | Must Have |

Sprint 2 Demo Scenarios:

- Demo 1: User logs in with Google, profile auto-populates

- Demo 2: User searches 'هاتف' (phone), sees Arabic results

- Demo 3: User applies price filter 5000-20000 SYP, sees filtered results

- Demo 4: User views product detail page with images and specs

## 4.4 Sprint 3: Shopping Cart

Duration: Week 5-6 | Points: 70

Sprint Goal: Users can add items to cart, manage cart, and save addresses.

Stories Included:

| ID | Title | Points | Team | Priority |
| --- | --- | --- | --- | --- |
| SS-AUTH-009 | Guest Session Creation | 5 | BE+FE | Must Have |
| SS-USER-005 | Manage Address Book | 8 | BE+FE | Must Have |
| SS-USER-006 | Account Preferences | 3 | BE+FE | Should Have |
| SS-PROD-008 | Product Image Gallery | 5 | FE | Must Have |
| SS-PROD-009 | Product Variants Selection | 8 | BE+FE | Must Have |
| SS-CAT-005 | Mobile Category Navigation | 5 | FE | Must Have |
| SS-CAT-006 | Category Search | 3 | BE+FE | Should Have |
| SS-CART-001 | Add Product to Cart | 5 | BE+FE | Must Have |
| SS-CART-002 | Update Cart Item Quantity | 5 | BE+FE | Must Have |
| SS-CART-003 | Remove Item from Cart | 3 | BE+FE | Must Have |
| SS-CART-004 | View Cart Summary | 5 | BE+FE | Must Have |
| SS-CART-005 | Guest Cart | 8 | BE+FE | Must Have |
| SS-CART-008 | Cart Persistence | 5 | BE+FE | Must Have |
| SS-ADDR-001 | Add New Address | 5 | BE+FE | Must Have |
| SS-ADDR-002 | Syrian Governorate Hierarchy | 8 | BE+FE | Must Have |

Sprint 3 Demo Scenarios:

- Demo 1: Guest adds items to cart, cart persists on page refresh

- Demo 2: User selects product variant (color/size), price updates

- Demo 3: User adds Syrian address with Damascus governorate hierarchy

- Demo 4: Cart shows summary with subtotal in SYP

## 4.5 Sprint 4: Checkout

Duration: Week 7-8 | Points: 75

Sprint Goal: Users can complete full checkout flow and place orders.

Stories Included:

| ID | Title | Points | Team | Priority |
| --- | --- | --- | --- | --- |
| SS-CART-006 | Cart Merge on Login | 8 | BE | Must Have |
| SS-CART-007 | Cart Validation (Stock Check) | 5 | BE+FE | Must Have |
| SS-CART-010 | Mini Cart in Header | 5 | FE | Must Have |
| SS-CART-011 | Cart Empty State | 2 | FE | Must Have |
| SS-ORDER-001 | Select Shipping Address | 5 | BE+FE | Must Have |
| SS-ORDER-002 | Select Shipping Method | 5 | BE+FE | Must Have |
| SS-ORDER-003 | Select Payment Method | 5 | BE+FE | Must Have |
| SS-ORDER-004 | Order Summary Review | 3 | FE | Must Have |
| SS-ORDER-005 | Place Order | 8 | BE+FE | Must Have |
| SS-ORDER-006 | Order Confirmation Page | 3 | FE | Must Have |
| SS-PAY-001 | Pay with Cash on Delivery | 3 | BE+FE | Must Have |
| SS-PAY-002 | Pay with Bank Transfer | 5 | BE+FE | Must Have |
| SS-PAY-005 | Payment Failure Handling | 3 | BE+FE | Must Have |
| SS-PAY-006 | Order Total Calculation | 5 | BE | Must Have |
| SS-SHIP-001 | Calculate Shipping Cost | 5 | BE+FE | Must Have |
| SS-SHIP-003 | Syrian Shipping Config | 8 | BE | Must Have |

Sprint 4 Demo Scenarios:

- Demo 1: Full checkout flow - address, shipping, payment, review, place order

- Demo 2: Guest cart merges with user cart on login

- Demo 3: COD order with order confirmation page

- Demo 4: Shipping cost calculates based on Damascus vs Aleppo

## 4.6 Sprint 5: Order Management

Duration: Week 9-10 | Points: 70

Sprint Goal: Users can track orders and receive email notifications.

Stories Included:

| ID | Title | Points | Team | Priority |
| --- | --- | --- | --- | --- |
| SS-USER-004 | View Order History | 5 | BE+FE | Must Have |
| SS-PROD-010 | Recently Viewed Products | 5 | FE | Should Have |
| SS-PROD-005 | Filter by Brand | 3 | BE+FE | Should Have |
| SS-PROD-012 | Product Stock Status Display | 3 | BE+FE | Must Have |
| SS-CART-009 | Apply Promo Code | 8 | BE+FE | Should Have |
| SS-ORDER-007 | Order Status Tracking | 5 | BE+FE | Must Have |
| SS-ORDER-008 | View Order Details | 5 | BE+FE | Must Have |
| SS-ORDER-009 | Cancel Order | 5 | BE+FE | Should Have |
| SS-ORDER-010 | Order Email Notifications | 5 | BE | Must Have |
| SS-PAY-003 | Payment Confirmation (Admin) | 5 | BE+FE | Must Have |
| SS-PAY-004 | View Payment History | 3 | BE+FE | Should Have |
| SS-SHIP-002 | Track Shipment Status | 5 | BE+FE | Must Have |
| SS-SHIP-004 | Delivery Time Estimation | 3 | BE | Should Have |
| SS-SHIP-005 | Shipping Status Notifications | 5 | BE | Should Have |

Sprint 5 Demo Scenarios:

- Demo 1: User views order history with status timeline

- Demo 2: Email notification received on order status change

- Demo 3: Admin confirms bank transfer payment

- Demo 4: User applies promo code, discount reflected

## 4.7 Sprint 6: Polish & Launch Prep

Duration: Week 11-12 | Points: 45

Sprint Goal: System is QA-verified, performant, and ready for beta launch.

Stories Included:

| ID | Title | Points | Team | Priority |
| --- | --- | --- | --- | --- |
| SS-USER-007 | Delete Account Flow | 5 | BE | Could Have |
| SS-PROD-011 | Share Product | 3 | FE | Could Have |
| SS-ADDR-003 | Edit Existing Address | 3 | BE+FE | Must Have |
| SS-ADDR-004 | Delete Address | 2 | BE+FE | Must Have |
| SS-ADDR-005 | Set Default Address | 3 | BE+FE | Must Have |
| SS-ADDR-006 | Address Validation | 3 | BE+FE | Must Have |
| QA-001 | E2E Test Suite Completion | 8 | QA | Must Have |
| QA-002 | Performance Testing | 5 | QA | Must Have |
| QA-003 | Security Audit | 8 | QA | Must Have |
| INFRA-002 | Production Deployment | 5 | DevOps | Must Have |

Sprint 6 Focus:

- Bug fixes from Sprint 4-5 integration testing

- Performance optimization (API response < 200ms p95)

- Security hardening (OWASP top 10 verification)

- Load testing (100 concurrent users)

- Production deployment preparation

# SECTION 5: RISK REGISTER

Risk Assessment Matrix: Probability (L/M/H) × Impact (L/M/H/C)

| # | Risk | Prob | Impact | Mitigation Strategy | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Syrian internet instability affects user experience | High | High | Implement offline-first architecture, aggressive caching, lazy loading, service worker | FE Lead | Active |
| R2 | Payment gateway sanctions / unavailability | High | Critical | Focus on COD and bank transfer (no international gateways), document alternative Syrian payment providers | BE Lead | Active |
| R3 | Currency volatility (SYP fluctuation) | High | Medium | Store prices in both SYP and stable currency (USD), allow admin to bulk update prices | PO | Monitoring |
| R4 | Team member attrition during project | Medium | High | Document all code thoroughly, pair programming, no single points of failure, cross-training | PM | Active |
| R5 | Scope creep from stakeholders | High | Medium | Strict change control process, MVP-only commitment, defer features to MVP2 | PM/PO | Active |
| R6 | Integration issues between FE and BE teams | Medium | Medium | API contract-first development, Swagger/OpenAPI specs, weekly sync meetings | Tech Leads | Active |
| R7 | Performance issues at scale | Medium | High | Load testing from Sprint 4, Redis caching, database indexing, CDN for static assets | BE Lead | Planned |
| R8 | Security vulnerabilities | Medium | Critical | OWASP security checklist, dependency scanning, penetration testing in Sprint 6 | QA Lead | Planned |
| R9 | RTL/Arabic rendering issues across browsers | Medium | Medium | Cross-browser testing matrix, use established RTL patterns, test on actual Syrian devices | FE Lead | Active |
| R10 | Database migration failures | Low | High | Backup before migration, rollback scripts, test migrations on staging first | DBA | Active |
| R11 | Third-party service outages (email, OAuth) | Medium | Medium | Graceful degradation, retry logic, fallback to email/password auth | BE Lead | Active |
| R12 | Inadequate test coverage leading to bugs | Medium | High | 80% coverage requirement, PR blocking on test failures, dedicated QA team | QA Lead | Active |
| R13 | Delayed design deliverables blocking FE | Medium | Medium | Design sprint buffer, design one sprint ahead, use placeholder designs | UX Lead | Active |
| R14 | Server infrastructure costs exceed budget | Low | Medium | Cloud cost monitoring, auto-scaling limits, optimize queries before scaling | DevOps | Monitoring |
| R15 | Regulatory compliance issues (Syrian law) | Low | High | Legal consultation, KYC preparation for MVP2, data localization research | PO | Planned |

# SECTION 6: TOOLS & PROCESSES

## 6.1 Project Management Tools

| Purpose | Tool | Configuration |
| --- | --- | --- |
| Project Tracking | Jira Cloud | Board per team (FE, BE, QA), Epics for modules, custom fields for MVP phase |
| Source Control | GitHub | Branch protection, required reviews, status checks |
| CI/CD | GitHub Actions | Lint → Test → Build → Deploy to staging on develop merge |
| Communication | Slack | #souqsyria-general, #frontend-dev, #backend-dev, #qa, #blockers |
| Video Calls | Google Meet | Daily standups, Sprint ceremonies |
| Design | Figma | Component library, handoff specs, prototypes |
| Documentation | Notion | Architecture docs, ADRs, runbooks |
| API Testing | Swagger UI + Postman | API collections per module, environment configs |
| Monitoring | Sentry | Error tracking, performance monitoring |
| Database | phpMyAdmin | Dev environment, MySQL Workbench for DBA |

## 6.2 Git Workflow

Branch Structure:

main (production) ← staging ← develop ← feature/SS-XXX-NNN-description

Branch Naming: [type]/[story-id]-[short-description]

Examples:

- feature/SS-AUTH-001-email-registration

- fix/SS-CART-003-remove-item-error

- hotfix/SS-PAY-001-cod-calculation

Commit Format: Conventional Commits (enforced via commitlint)

Examples:

- feat(auth): implement OTP verification [SS-AUTH-001]

- fix(cart): resolve quantity update race condition [SS-CART-002]

- docs(api): update Swagger for order endpoints

## 6.3 Definition of Ready Checklist

- ☐ User story follows INVEST criteria

- ☐ Acceptance criteria in Given/When/Then format

- ☐ Story points estimated (Planning Poker)

- ☐ UI mockup approved (if applicable)

- ☐ API contract defined (OpenAPI spec)

- ☐ Dependencies identified and scheduled

- ☐ Fits within one sprint

## 6.4 Definition of Done Checklist

- ☐ Code written and peer-reviewed (1 Senior + Lead approval)

- ☐ Unit tests passing (>80% coverage)

- ☐ Integration tests passing

- ☐ Swagger documentation updated

- ☐ No ESLint/Prettier warnings

- ☐ Conventional commit messages

- ☐ Deployed to staging

- ☐ QA verified on staging

- ☐ Product Owner accepted

# SECTION 7: SUCCESS METRICS & KPIs

## 7.1 Delivery Metrics (Sprint-level)

| Metric | Target | Measurement | Owner |
| --- | --- | --- | --- |
| Sprint Velocity | Within ±10% of average | Story points completed vs committed | PM |
| Sprint Goal Completion | >85% | % of sprint goal achieved | PM |
| Carryover Rate | <15% | Stories not completed / total stories | PM |
| Blocked Items | <3 per sprint | Stories blocked for >2 days | PM |
| Code Review Turnaround | <24 hours | PR open to first review | Tech Leads |
| Deployment Frequency | 1+ per sprint | Successful staging deployments | DevOps |

## 7.2 Quality Metrics

| Metric | Target | Measurement | Owner |
| --- | --- | --- | --- |
| Test Coverage | >80% | Jest + Karma coverage reports | QA Lead |
| Bug Escape Rate | <5% | Bugs found in production / total bugs | QA Lead |
| Defect Density | <0.5 bugs per story | Bugs found / stories completed | QA Lead |
| Critical Bugs | 0 in production | P1 bugs in prod | QA Lead |
| Regression Rate | <10% | Bugs reintroduced after fix | QA Lead |

## 7.3 Technical Metrics

| Metric | Target | Measurement | Owner |
| --- | --- | --- | --- |
| API Response Time | <200ms p95 | Backend API latency | BE Lead |
| Frontend Load Time | <3s | Time to interactive | FE Lead |
| LCP (Largest Contentful Paint) | <2.5s | Core Web Vitals | FE Lead |
| FID (First Input Delay) | <100ms | Core Web Vitals | FE Lead |
| CLS (Cumulative Layout Shift) | <0.1 | Core Web Vitals | FE Lead |
| Error Rate | <0.1% | Sentry error count / requests | DevOps |
| Uptime | >99.5% | Monitoring alerts | DevOps |

## 7.4 MVP1 Launch Success Criteria

MVP1 is considered successful when:

- ✓ All 'Must Have' stories completed and accepted

- ✓ Zero critical (P1) bugs in staging

- ✓ All E2E test scenarios passing

- ✓ Performance targets met (API <200ms, FE <3s)

- ✓ Security audit passed (no critical vulnerabilities)

- ✓ 10 beta users complete full purchase flow successfully

- ✓ Arabic RTL rendering verified on Chrome, Firefox, Safari

# SECTION 8: GLOSSARY (Arabic/English)

| English Term | Arabic Term | Description |
| --- | --- | --- |
| Cart | سلة التسوق | Shopping cart for collecting items |
| Checkout | إتمام الشراء | Order completion process |
| Order | طلب | Confirmed purchase |
| Product | منتج | Item for sale |
| Category | فئة | Product grouping |
| Governorate | محافظة | Syrian administrative division |
| Cash on Delivery (COD) | الدفع عند الاستلام | Pay when order arrives |
| Bank Transfer | تحويل بنكي | Wire transfer payment |
| Shipping | الشحن | Order delivery |
| Address | عنوان | Delivery location |
| Account | حساب | User account |
| Login | تسجيل الدخول | Sign in to account |
| Register | تسجيل | Create new account |
| Password | كلمة المرور | Account password |
| Syrian Pound (SYP) | ليرة سورية | Syrian currency |

═══════════════════════════════════════════════════════════════════════

END OF MVP1 PROJECT MANAGEMENT DOCUMENTATION

Document Version: 1.0 | Generated: February 2026

Next Phase: MVP2 - Vendor Ecosystem & Advanced Admin (Sprints 7-12)

═══════════════════════════════════════════════════════════════════════